## Arkusz1
Task | Start week | Duration | End Week | Order
Requirements analysis | 1 | 1 | 2 | 1
Hardware & software selection | 2 | 1 | 2 | 2
Software configuration | 2 | 2 | 2 | 3
Arduino configuration | 2 | 1 | 2 | 4
Sensors configuration | 16 | 1 | 17 | 5
WeMos configuration | 2 | 1 | 2 | 6
Connecting WeMos to the network | 3 | 1 | 3 | 8
Connecting WeMos to the database | 3 | 1 | 3 | 9
Performing tests | 4 | 2 | 6 | 10
Preparing Customer Pitch | 1 | 3 | 4 | 11
Preparing the Project Proposal | 1 | 8 | 9 | 12
Delivering Customer Pitch | 7 | 1 | 7 | 13
Customer Pitch presentation | 7 | 1 | 7 | 14
Comparing the Project Proposal with the template | 9 | 1 | 9 | 15
Delivering documentation | 10 | 1 | 10 | 16
Consultation | 10 | 1 | 10 | 17
Preparing Prototype | 4 | 9 | 12 | 18
Initial tests & implementing necessary changes | 13 | 1 | 14 | 19
Tests performed in the client presence | 14 | 1 | 14 | 20
Consultation | 15 | 1 | 15 | 21
Accomodating the client's needs in the Prototype | 16 | 2 | 18 | 22
Performing tests in the client presence | 18 | 1 | 19 | 23
Consultation | 19 | 1 | 19 | 24
Preparing the online control interface | 20 | 2 | 22 | 25
Connecting the interface to the main system | 22 | 1 | 23 | 26
Initial tests & implementing necessary changes | 23 | 1 | 23 | 27
Tests performed in the client presence | 24 | 1 | 24 | 28
Consultation | 24 | 1 | 24 | 29
Preparation of the data analysis charts | 24 | 1 | 24 | 30
Building Final Prototype | 25 | 1 | 26 | 31
Performing tests in the client presence | 26 | 1 | 26 | 32
Consultation | 26 | 1 | 26 | 33
Implementing the prototype as a final product | 27 | 1 | 27 | 34
Formulas:
Duration = DAYS([End Week],[Start week])