## Arkusz1
Task | Start week | Duration | End Week | Order
Preparing the Project Proposal | 1 | 8 | 9 | 1
Requirements analysis | 1 | 1 | 2 | 2
Hardware & software selection | 2 | 1 | 2 | 3
Software configuration | 2 | 2 | 2 | 4
Arduino configuration | 2 | 1 | 2 | 5
WeMos configuration | 2 | 1 | 2 | 6
Connecting WeMos to the network | 3 | 1 | 3 | 7
Connecting WeMos to the database | 3 | 1 | 3 | 8
Hardware testing | 4 | 2 | 6 | 9
Preparing Client Pitch | 1 | 6 | 6 | 10
Delivering Client Pitch | 7 | 1 | 7 | 11
Client Consultation | 9 | 20 | 29 | 13
Delivering documentation | 10 | 1 | 10 | 12
Developing Prototypes | 4 | 24 | 27 | 14
Performing tests in the client presence | 18 | 1 | 19 | 17 | Develop database | 17 | 2 | 19 | 20
Develop database | 17 | 2 | 19 | 20
Develop the website | 17 | 11 | 28 | 19
Develop the Arduino Subsystem | 17 | 10 | 27 | 21
Write White Paper | 24 | 1 | 24 | 22
Assembling Final Prototype | 25 | 4 | 29 | 25
Formulas:
Duration = DAYS([End Week],[Start week])